## Claims register
CLAIMS REGISTER
One row per payment claim, sent or received. Type or paste into the white columns (A to P); the shaded columns are formulas.
Claim no | Direction | Contract | Claimant | Payer | Period end | Date served | Schedule due | Payment due | Claimed (ex GST) | Scheduled (ex GST) | Paid (ex GST) | Date paid | Retention held this claim | Retention released | Notes | Variance (claimed less scheduled) | Unpaid | Retention held to date (this contract) | Variations approved $ | Variations pending $ | Status
PC-03 | Sent | Example (made up): framing, 12 Example Street | Sample Framing Co | Sample Builders | 2026-08-31 | 2026-09-01 | 2026-09-29 | 2026-09-29 | 24000 | 22500 | 22500 | 2026-09-28 | 1125 | 0 | Example (made up): 1,500 of day works not agreed
PC-04 | Sent | Example (made up): framing, 12 Example Street | Sample Framing Co | Sample Builders | 2026-09-30 | 2026-10-01 | 2026-10-30 | 2026-10-30 | 18000 | 18000 |  |  | 900 | 0 | Example (made up)
SC-07 | Received | Example (made up): electrical, 12 Example Street | Sample Sparks | Sample Builders | 2026-10-31 | 2026-11-02 | 2026-11-30 | 2026-11-30 | 9500 | [5 empty] | Example (made up): schedule to send
Status is worked out from today's date: Paid, Scheduled at $0, Schedule date passed: none recorded, Payment overdue, or Open. It's a reminder to check, not a decision on what is owed.
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.
Formulas:
Status = IF([Claim no]="","",IF(AND([Paid (ex GST)]<>"",[Paid (ex GST)]>=IF([Scheduled (ex GST)]="",[Claimed (ex GST)],[Scheduled (ex GST)])),"Paid",IF(AND([Scheduled (ex GST)]<>"",[Scheduled (ex GST)]=0),"Scheduled at $0",IF(AND([Scheduled (ex GST)]="",[Schedule due]<>"",TODAY()>[Schedule due]),"Schedule date passed: none recorded",IF(AND([Payment due]<>"",TODAY()>[Payment due]),"Payment overdue","Open")))))

## Variations
VARIATIONS
The variations register's columns, plus the contract and the claim each variation is in. Totals flow to the Claims register.
Var no | Rev | Description | Instruction / ref | Submitted | Approved | Status | Quoted $ | Approved $ | Claimed to date $ | Notes | Contract | Claim no
V01 | A | Example (made up): extra blocking to kitchen wall | SI-004 | 2026-10-02 | 2026-10-09 | Approved | 1850 | 1850 | 1850 | Approved in writing by the site manager | Example (made up): framing, 12 Example Street | PC-04
V02 | A | Example (made up): relocate two power points | Email 12 Oct | 2026-10-13 |  | Pending | 640 |  |  | Waiting on written approval | Example (made up): framing, 12 Example Street | PC-04

## Summary
SUMMARY
From the Claims register. Formulas only.
| Claims sent | Claims received
Claimed (ex GST)
Scheduled (ex GST)
Paid (ex GST)
Variance (claimed less scheduled)
Unpaid
Retention held this claim, total
Retention released, total
Variations approved $
Variations pending $
Payment overdue (count)
Schedule date passed, none recorded (count)
Dates: Construction Contracts Act 2002, s22(b) (payment schedule) and s18 (payment), 20 working days unless the contract says otherwise. Source: legislation.govt.nz, checked 1 Nov 2026.
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.