## Procurement
PROCUREMENT
Orders and subcontracts. A claim received names its order ID in the Claims sheet. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Order ID | Type | Supplier or subcontractor | Description | Date placed | Committed value | Retention % | Forecast final (yours) | Claimed (from Claims) | Paid (from Claims) | Retention held (from Retention) | Committed, not yet claimed | Forecast less committed
PO-001 | Subcontract | Sample Sparks | Electrical rough-in and fit-off | 2026-08-20 | 48000 | 5 | 49500
PO-002 | Subcontract | Sample Framing Co | Framing labour | 2026-08-25 | 62000 | 5
PO-003 | Order | Sample Timber Supplies | Framing timber | 2026-09-10 | 28400 |  | 28400
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Claims
CLAIMS
The claims register's columns (sent and received), then the order ID. Rows paste from any tool's register CSV. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Claim no | Direction | Contract | Claimant | Payer | Period end | Date served | Schedule due | Payment due | Claimed (ex GST) | Scheduled (ex GST) | Paid (ex GST) | Date paid | Retention held this claim | Retention released | Notes | Order ID | Scheduled (used) | Paid (used) | Variance (claimed less scheduled) | Unpaid (after retention held) | Status
PC-01 | Sent | 12 Example Street townhouses (made-up sample) | Sample Builders | Sample Developments | 2026-09-30 | 2026-10-01 | 2026-10-30 | 2026-10-30 | 77700 | 77700 | 73815 | 2026-10-29 | 3885 | 0
PC-02 | Sent | 12 Example Street townhouses (made-up sample) | Sample Builders | Sample Developments | 2026-10-31 | 2026-11-02 | 2026-11-30 | 2026-11-30 | 68020
SC-05 | Received | 12 Example Street townhouses (made-up sample) | Sample Sparks | Sample Builders | 2026-08-31 | 2026-09-01 | 2026-09-29 | 2026-09-29 | 6000 | [6 empty] | PO-001
SF-03 | Received | 12 Example Street townhouses (made-up sample) | Sample Framing Co | Sample Builders | 2026-09-30 | 2026-10-01 | 2026-10-30 | 2026-10-30 | 24000 | 22500 | 21375 | 2026-10-29 | 1125 | 0 |  | PO-002
SC-07 | Received | 12 Example Street townhouses (made-up sample) | Sample Sparks | Sample Builders | 2026-10-31 | 2026-11-02 | 2026-11-30 | 2026-11-30 | 9500 | [6 empty] | PO-001
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.
Formulas:
Status = IF([Claim no]="","",IF(AND(N([Paid (used)])>0,N([Paid (used)])+N([Retention held this claim])>=IF([Scheduled (used)]="",[Claimed (ex GST)],[Scheduled (used)])-0.005),"Paid",IF(AND([Scheduled (used)]="",[Schedule due]<>"",TODAY()>[Schedule due]),"Schedule date passed: none recorded",IF(AND([Payment due]<>"",TODAY()>[Payment due]),"Payment date passed: not paid in full",IF([Scheduled (used)]<>"","Scheduled","Open")))))

## Retention
RETENTION
Retention held and released, by claim, order and party, with the date of each retention report. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Retention ID | Claim no | Order ID | Party | Date | Held this claim | Released | Report given | Balance held for this party to date | 3 months after the report (s18FD(1)(b))
R-001 | PC-01 |  | Sample Builders | 2026-10-29 | 3885 | 0 | 2026-10-29
R-002 | SF-03 | PO-002 | Sample Framing Co | 2026-10-29 | 1125 | 0 | 2026-07-15
R-003 |  | PO-001 | Sample Sparks | 2026-08-29 | 300 | 0
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.