## Items
ITEMS
The contract items, with quantities and rates. Item IDs (IT-001) join every sheet. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Item ID | Description | Unit | Contract qty | Rate | Programme start | Programme finish | Contract value | Measured qty to date | % complete | Value to date | Claimed to date (claim lines) | Measured, not yet claimed
IT-001 | Foundations and slab | m² | 420 | 185 | 2026-09-01 | 2026-09-30
IT-002 | Wall and roof framing | m² | 860 | 95 | 2026-10-01 | 2026-11-20
IT-003 | Roofing | m² | 380 | 120 | 2026-11-02 | 2026-11-27
IT-004 | Electrical rough-in | each | 6 | 9500 | 2026-10-19 | 2026-12-04
IT-005 | Cladding | m² | 640 | 140 | 2026-11-16 | 2026-12-18
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Measurement
MEASUREMENT
One row per measurement: the quantity measured that time. The diary ID and photo references back it up. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Measurement ID | Date | Item ID | Qty measured | Area or location | Diary ID | Photo refs | Measured by | Notes | Rate (from Items) | Value measured
M-001 | 2026-09-25 | IT-001 | 420 | Blocks A and B | D-001 | P-0101 | Sample site engineer
M-002 | 2026-10-16 | IT-002 | 300 | Level 1, blocks A and B | D-004 | P-0144 | Sample site engineer
M-003 | 2026-10-30 | IT-002 | 216 | Roof, block A | D-006 | P-0160 | Sample site engineer
M-004 | 2026-10-30 | IT-004 | 2 | Units 1 and 2 | D-006 | P-0161 | Sample site engineer
M-005 | 2026-11-04 | IT-002 | 120 | Block B | D-008 | P-0175 | Sample site engineer
M-006 | 2026-11-05 | IT-003 | 95 | Roof, block A |  |  | Sample site engineer
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Claim lines
CLAIM LINES
One row per line of each claim, with the measurements behind it. Exported by the progress measurement sheet. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Claim no | Item ID | Description | % complete | Value to date | Previously claimed | This claim | Measurement IDs | Measurement named | Check: to date less before less this claim (0)
PC-01 | IT-001 | Foundations and slab | 1 | 77700 | 0 | 77700 | M-001
PC-02 | IT-001 | Foundations and slab | 1 | 77700 | 77700 | 0 | M-001
PC-02 | IT-002 | Wall and roof framing | 0.6 | 49020 | 0 | 49020 | M-002, M-003
PC-02 | IT-004 | Electrical rough-in | 0.3333 | 19000 | 0 | 19000 | M-004
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.