## Summary
PROJECT WORKBOOK
12 Example Street townhouses (made-up sample). Formulas only: every figure comes from the sheets. Example rows are made up.
Figure
Contract value (Items)
Value measured to date (Items)
Claimed by us: claims sent (Claims)
Scheduled on claims sent
Paid on claims sent
Claimed from us: claims received
Scheduled on claims received
Paid on claims received
Retention held, all parties (Retention)
Variations approved $ (Variations)
Variations waiting on a decision, quoted $
Variations with no notice date (count)
RFIs open (count)
RFIs overdue, unanswered (count)
Committed on orders and subcontracts (Procurement)
Claimed against orders and subcontracts
Claims: schedule date passed, none recorded (count)
Claims: payment date passed, not paid in full (count)
Measurements with no diary ID (count)
Site diary entries (count)
Transmittals (count)
Original budget (Budget)
Current budget, after approved changes
Contingency left
Cash flow forecast, net (Cash flow)
Live risks rated Extreme or High (count)
How it links: Items → Measurement → Claim lines → Claims → Schedules → Payments and Retention, with Variations, RFIs, Procurement, Transmittals and the Diary index joined by their IDs. Each tool's CSV export pastes into its own sheet at cell A5.
Dates: Construction Contracts Act 2002, s22(b) (payment schedule) and s18 (payment), 20 working days unless the contract says otherwise. Retention reports: s18FD(1)(b), "at least once in every 3 months". Source: legislation.govt.nz, checked 1 Nov 2026.
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Items
ITEMS
The contract items, with quantities and rates. Item IDs (IT-001) join every sheet. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Item ID | Description | Unit | Contract qty | Rate | Programme start | Programme finish | Contract value | Measured qty to date | % complete | Value to date | Claimed to date (claim lines) | Measured, not yet claimed
IT-001 | Foundations and slab | m² | 420 | 185 | 2026-09-01 | 2026-09-30
IT-002 | Wall and roof framing | m² | 860 | 95 | 2026-10-01 | 2026-11-20
IT-003 | Roofing | m² | 380 | 120 | 2026-11-02 | 2026-11-27
IT-004 | Electrical rough-in | each | 6 | 9500 | 2026-10-19 | 2026-12-04
IT-005 | Cladding | m² | 640 | 140 | 2026-11-16 | 2026-12-18
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Measurement
MEASUREMENT
One row per measurement: the quantity measured that time. The diary ID and photo references back it up. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Measurement ID | Date | Item ID | Qty measured | Area or location | Diary ID | Photo refs | Measured by | Notes | Rate (from Items) | Value measured | Diary entry found
M-001 | 2026-09-25 | IT-001 | 420 | Blocks A and B | D-001 | P-0101 | Sample site engineer
M-002 | 2026-10-16 | IT-002 | 300 | Level 1, blocks A and B | D-004 | P-0144 | Sample site engineer
M-003 | 2026-10-30 | IT-002 | 216 | Roof, block A | D-006 | P-0160 | Sample site engineer
M-004 | 2026-10-30 | IT-004 | 2 | Units 1 and 2 | D-006 | P-0161 | Sample site engineer
M-005 | 2026-11-04 | IT-002 | 120 | Block B | D-008 | P-0175 | Sample site engineer
M-006 | 2026-11-05 | IT-003 | 95 | Roof, block A |  |  | Sample site engineer
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Claim lines
CLAIM LINES
One row per line of each claim, with the measurements behind it. Exported by the progress measurement sheet. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Claim no | Item ID | Description | % complete | Value to date | Previously claimed | This claim | Measurement IDs | Measurement named | Check: to date less before less this claim (0)
PC-01 | IT-001 | Foundations and slab | 1 | 77700 | 0 | 77700 | M-001
PC-02 | IT-001 | Foundations and slab | 1 | 77700 | 77700 | 0 | M-001
PC-02 | IT-002 | Wall and roof framing | 0.6 | 49020 | 0 | 49020 | M-002, M-003
PC-02 | IT-004 | Electrical rough-in | 0.3333 | 19000 | 0 | 19000 | M-004
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Claims
CLAIMS
The claims register's columns (sent and received), then the order ID. Rows paste from any tool's register CSV. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Claim no | Direction | Contract | Claimant | Payer | Period end | Date served | Schedule due | Payment due | Claimed (ex GST) | Scheduled (ex GST) | Paid (ex GST) | Date paid | Retention held this claim | Retention released | Notes | Order ID | Claim lines total | Scheduled (used) | Paid (used) | Variance (claimed less scheduled) | Unpaid (after retention held) | Status
PC-01 | Sent | 12 Example Street townhouses (made-up sample) | Sample Builders | Sample Developments | 2026-09-30 | 2026-10-01 | 2026-10-30 | 2026-10-30 | 77700 | 77700 | 73815 | 2026-10-29 | 3885 | 0
PC-02 | Sent | 12 Example Street townhouses (made-up sample) | Sample Builders | Sample Developments | 2026-10-31 | 2026-11-02 | 2026-11-30 | 2026-11-30 | 68020
SC-05 | Received | 12 Example Street townhouses (made-up sample) | Sample Sparks | Sample Builders | 2026-08-31 | 2026-09-01 | 2026-09-29 | 2026-09-29 | 6000 | [6 empty] | PO-001
SF-03 | Received | 12 Example Street townhouses (made-up sample) | Sample Framing Co | Sample Builders | 2026-09-30 | 2026-10-01 | 2026-10-30 | 2026-10-30 | 24000 | 22500 | 21375 | 2026-10-29 | 1125 | 0 |  | PO-002
SC-07 | Received | 12 Example Street townhouses (made-up sample) | Sample Sparks | Sample Builders | 2026-10-31 | 2026-11-02 | 2026-11-30 | 2026-11-30 | 9500 | [6 empty] | PO-001
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.
Formulas:
Status = IF([Claim no]="","",IF(AND(N([Paid (used)])>0,N([Paid (used)])+N([Retention held this claim])>=IF([Scheduled (used)]="",[Claimed (ex GST)],[Scheduled (used)])-0.005),"Paid",IF(AND([Scheduled (used)]="",[Schedule due]<>"",TODAY()>[Schedule due]),"Schedule date passed: none recorded",IF(AND([Payment due]<>"",TODAY()>[Payment due]),"Payment date passed: not paid in full",IF([Scheduled (used)]<>"","Scheduled","Open")))))

## Schedules
SCHEDULES
Payment schedules, by the claim they answer. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Schedule ID | Claim no | Date of schedule | Date served | Claimed | Scheduled | Reasons | Difference (claimed less scheduled) | Claim found
PS-001 | PC-01 | 2026-10-20 | 2026-10-20 | 77700 | 77700
PS-002 | SF-03 | 2026-10-20 | 2026-10-20 | 24000 | 22500 | $1,500 of day works not agreed: variation V02 still pending.
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Payments
PAYMENTS
Payments, by the claim paid. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Payment ID | Claim no | Date paid | Amount paid (ex GST) | Reference | Claim found
PAY-001 | PC-01 | 2026-10-29 | 73815 | Sample Developments remittance 5531 (after 5% retention)
PAY-002 | SF-03 | 2026-10-29 | 21375 | Payment run 29 Oct (after 5% retention)
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Retention
RETENTION
Retention held and released, by claim, order and party, with the date of each retention report. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Retention ID | Claim no | Order ID | Party | Date | Held this claim | Released | Report given | Balance held for this party to date | 3 months after the report (s18FD(1)(b))
R-001 | PC-01 |  | Sample Builders | 2026-10-29 | 3885 | 0 | 2026-10-29
R-002 | SF-03 | PO-002 | Sample Framing Co | 2026-10-29 | 1125 | 0 | 2026-07-15
R-003 |  | PO-001 | Sample Sparks | 2026-08-29 | 300 | 0
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Variations
VARIATIONS
The variations register, with the notice date, the RFI and the item each one comes from. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Var no | Rev | Description | Instruction / ref | Submitted | Approved | Status | Quoted $ | Approved $ | Claimed to date $ | Notes | Contract | Claim no | Notice date | RFI ID | Item ID | Diary ID | Notice recorded | RFI found
V01 | A | Extra blocking to kitchen walls | SI-004 | 2026-10-02 | 2026-10-09 | Approved | 1850 | 1850 |  |  | 12 Example Street townhouses (made-up sample) |  | 2026-10-02 | RFI-001 | IT-002 | D-004
V02 | A | Relocate power points, units 3 to 6 | Email 12 Oct | 2026-10-13 |  | Pending | 640 |  |  |  | 12 Example Street townhouses (made-up sample) |  |  | RFI-002 | IT-004
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## RFIs
RFIS
RFIs and technical queries. A variation that comes from one names its RFI ID. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
RFI ID | Date raised | Raised by | To | Question | Item ID | Response needed by | Date answered | Response | Variation ID | Status
RFI-001 | 2026-09-28 | Sample site engineer | Sample Design (engineer) | Kitchen wall cabinets: what blocking is needed? | IT-002 | 2026-10-02 | 2026-10-01 | Two rows of 90 x 45 blocking, see SI-004. | V01
RFI-002 | 2026-10-12 | Sample Sparks | Sample Design (engineer) | Units 3 to 6: confirm the new power point positions. | IT-004 | 2026-10-19 |  |  | V02
RFI-003 | 2026-11-04 | Sample site manager | Sample Design (engineer) | Cladding: cavity batten spacing at the corners. | IT-005 | 2026-11-13
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.
Formulas:
Status = IF([RFI ID]="","",IF([Date answered]<>"","Answered",IF(AND([Response needed by]<>"",TODAY()>[Response needed by]),"Overdue: unanswered","Open")))

## Procurement
PROCUREMENT
Orders and subcontracts. A claim received names its order ID in the Claims sheet. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Order ID | Type | Supplier or subcontractor | Description | Date placed | Committed value | Retention % | Forecast final (yours) | Claimed (from Claims) | Paid (from Claims) | Retention held (from Retention) | Committed, not yet claimed | Forecast less committed
PO-001 | Subcontract | Sample Sparks | Electrical rough-in and fit-off | 2026-08-20 | 48000 | 5 | 49500
PO-002 | Subcontract | Sample Framing Co | Framing labour | 2026-08-25 | 62000 | 5
PO-003 | Order | Sample Timber Supplies | Framing timber | 2026-09-10 | 28400 |  | 28400
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Transmittals
TRANSMITTALS
What was issued, to whom, when and how: the record of service for claims and schedules. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Transmittal ID | Date issued | Document | Number and revision | Issued to | How issued | Purpose | Related ID | Acknowledged | Notes | Days to acknowledge | Related record found
TR-001 | 2026-10-01 | Payment claim PC-01 with Form 1 | PC-01 rev 0 | Sample Developments | Email | Payment claim | PC-01 | 2026-10-01
TR-002 | 2026-10-20 | Payment schedule PS-002 | PS-002 rev 0 | Sample Framing Co | Delivered to the person | Payment schedule | PS-002 | 2026-10-20
TR-003 | 2026-11-02 | Payment claim PC-02 with Form 1 | PC-02 rev 0 | Sample Developments | Delivered to the person | Payment claim | PC-02
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Diary index
DIARY INDEX
One row per site diary entry, with the item IDs worked on and the photo references. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Diary ID | Date | Weather | Labour | People on site | Plant | Item IDs | Work done | Delays | Delay cause | Instructions | Visitors | Photo refs | Prepared by | Measurements naming this entry
D-001 | 2026-09-25 | Fine | Concrete crew 6, labourers 2 | 8 | Concrete pump, 5 t digger | IT-001 | Slab poured, blocks A and B. |  |  |  | Engineer's slab inspection (Sample Design) | P-0101, P-0102 | Sample site manager
D-004 | 2026-10-16 | Showers | Carpenters 5, labourers 1 | 6 | Telehandler | IT-002 | Level 1 walls framed, blocks A and B. | 1 hour lost to rain | Weather | SI-004: extra blocking to kitchen walls |  | P-0144 | Sample site manager
D-006 | 2026-10-30 | Fine | Carpenters 5, electricians 2 | 7 | Telehandler, scissor lift | IT-002, IT-004 | Roof trusses up, block A. Electrical rough-in, units 1 and 2. |  |  |  | Client's representative site walk | P-0160, P-0161 | Sample site manager
D-007 | 2026-11-02 | Wind | Carpenters 4, roofers 3 | 7 | Telehandler | IT-002, IT-003 | Framing, block B. Roofing started, block A. | Roofing stopped from 2 pm: wind over 50 km/h | Weather |  |  | P-0170 | Sample site manager
D-008 | 2026-11-04 | Fine | Carpenters 4, roofers 3 | 7 | Telehandler | IT-002, IT-003 | Framing, block B. Roofing, block A. |  |  | RFI-003 raised: cladding cavity battens |  | P-0175 | Sample site manager
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Budget
BUDGET
The budget by cost code, with the orders against each line. Contingency is a line of its own. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Budget ID | Cost code | Description | Category | Original budget | Order IDs | Manager | Notes | Forecast final (yours) | Approved changes | Current budget | Current budget less your forecast
B-001 | 01-100 | Preliminaries and site set-up | Preliminaries | 38000 |  | Sample project manager | Scaffold hire runs a month longer | 39500
B-002 | 04-100 | Framing labour | Subcontract | 60000 | PO-002 | Sample QS
B-003 | 04-200 | Framing timber | Materials | 30000 | PO-003 | Sample QS
B-004 | 05-200 | Electrical | Subcontract | 50000 | PO-001 | Sample QS
B-005 | 99-000 | Contingency | Contingency | 15000 |  | Sample cost controller
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Budget changes
BUDGET CHANGES
Each change to the budget: new money in, or money moved from one line (such as contingency) to another. Only approved changes count. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Change ID | Date | Budget ID | Change ($) | Moved from (budget ID) | Reason | Status | Variation ID | Approved by | Approved on | Budget line found
BCH-001 | 2026-08-26 | B-002 | 2000 | B-005 | Framing subcontract let above budget | Approved |  | Sample cost controller | 2026-08-26
BCH-002 | 2026-10-20 | B-004 | 1500 | B-005 | Extra switchboard capacity | Proposed | V02
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Cash flow
CASH FLOW
Your forecast of money in and out, by month. Actual payments are in the Payments sheet. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Forecast ID | Month | In or out | Forecast amount | Budget ID | Order ID | Basis | Net (in less out)
CF-001 | 2026-10 | In (income) | 84000 |  |  | PC-01 less retention
CF-002 | 2026-10 | Out (costs) | 22000 | B-002 | PO-002 | SF-03 less retention
CF-003 | 2026-11 | In (income) | 95000 |  |  | PC-02 as claimed, less retention
CF-004 | 2026-11 | Out (costs) | 41000 | B-004 | PO-001 | SC-07 and timber
CF-005 | 2026-12 | In (income) | 90000 |  |  | Roofing and cladding progress
CF-006 | 2026-12 | Out (costs) | 64000 | B-002 | PO-002 | Framing complete, roofing materials
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Risks
RISKS
The risk register. Rating is likelihood × consequence on a 5 by 5 scale: Extreme 15 to 25, High 10 to 14, Medium 5 to 9, Low 1 to 4. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Risk ID | Risk | Category | Cause | What would happen | Likelihood | Consequence | Treatment | Owner | Likelihood after | Consequence after | Cost if it happens | Delay (working days) | Raised | Next review | Status | Item ID | Rating now (likelihood × consequence) | Level | Rating after treatment
RK-001 | Roofing iron delivery slips past the programme | Supply chain | Long lead time on the colour chosen | Roofing starts late and the building isn't closed in | 3 Possible | 4 Major | Order confirmed with two suppliers; delivery checked weekly | Sample project manager | 2 Unlikely | 3 Moderate | 8000 | 10 | 2026-09-15 | 2026-11-10 | Open | IT-003
RK-002 | Wet weather during the slab pours | Site and ground | Spring rain | Pours rescheduled, trades stood down | 4 Likely | 2 Minor | Pour dates held loosely; covers on site | Sample site manager | 3 Possible | 2 Minor | 2500 | 4 | 2026-08-20 | 2026-10-20 | Being treated | IT-001
RK-003 | Framing subcontractor short of labour | Programme | Other jobs in the area | Framing runs past 20 November | 2 Unlikely | 4 Major |  |  |  |  | 12000 | 15 | 2026-10-05 | 2026-11-30 | Open | IT-002
RK-004 | Fall from height at the roof stage | Health and safety | Work at the roof edge | Serious harm to a worker | 2 Unlikely | 5 Severe | Scaffold with edge protection before roofing starts; daily checks | Sample site manager | 1 Rare | 5 Severe |  |  | 2026-10-01 | 2026-11-25 | Open | IT-003
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Programme
PROGRAMME
The programme, loaded from P6 (XER) or MS Project (XML) or typed in. Item IDs tie an activity to the contract items. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Activity ID | Programme ID | Activity | WBS or area | Planned start | Planned finish | Baseline finish | Actual start | Actual finish | % complete | Milestone | Critical | Item IDs | Status | Days past baseline
ACT-0001 | A1000 | Site establishment | Substructure | 2026-08-24 | 2026-08-28 |  | 2026-08-24 | 2026-08-28 | 100 | No | No
ACT-0002 | A1010 | Foundations and slab | Substructure | 2026-09-01 | 2026-10-02 |  | 2026-09-01 | 2026-10-02 | 100 | No | Yes | IT-001
ACT-0003 | A1020 | Wall and roof framing | Superstructure and envelope | 2026-10-05 | 2026-11-20 |  | 2026-10-05 |  | 62 | No | Yes | IT-002
ACT-0004 | A1030 | Roofing | Superstructure and envelope | 2026-11-02 | 2026-11-27 |  |  |  | 0 | No | Yes | IT-003
ACT-0005 | A1040 | Building closed in | Superstructure and envelope | 2026-11-27 | 2026-11-27 |  |  |  | 0 | Yes | Yes
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.
Formulas:
Status = IF([Activity ID]="","",IF([Actual finish]<>"","Finished",IF(AND([Planned finish]<>"",TODAY()>[Planned finish]),"Late","Open")))

## Supplier invoices
SUPPLIER INVOICES
Invoices from suppliers and subcontractors, each against its order. The app checks each one against the order, the claim and its schedule, the GST and repeats. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Invoice ID | Order ID | Supplier | Their invoice number | Invoice date | Due date | GST number | Before GST | GST | Total | Claim ID | What it's for | Status | Notes | GST check (15%) | Total check | Order found
BILL-001 | PO-002 | Sample Framing Co | SF-INV-031 | 2026-10-21 | 2026-10-29 | 00-000-111 (made up) | 21375 | 3206.25 | 24581.25 | SF-03 | Framing labour, September | Paid
BILL-002 | PO-003 | Sample Timber Supplies | 8812 | 2026-10-25 | 2026-11-20 |  | 14200 | 2130 | 16330 |  | Framing timber, second delivery | To check
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Plant
PLANT
Each machine by its fleet or asset number and registration, own or hired, with the hire order and rate. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Machine ID | Fleet or asset no. | Registration | Machine | Own or hired | Hire company | Hire order | Rate | Rate is | Minimum hours a day | On site from | Off site | Notes | Hours to date
PL-001 | EX-07 |  | 20 t excavator | Own fleet |  |  | 145 | per hour |  | 2026-09-01
PL-002 | RL-12 | KXR442 | 9 t smooth drum roller | Hired | Sample Plant Hire |  | 95 | per hour | 4 | 2026-09-08 | 2026-09-30
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.

## Plant hours
PLANT HOURS
One line a machine a day: the hour meter at start and finish (the hours are worked out from them), idle hours, the operator, the item and the diary entry. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Entry ID | Date | Machine ID | Meter start | Meter finish | Hours entered | Idle hours | Operator | Item ID | Diary ID | Docket | Notes | Hours (meter, else entered) | Check
PH-001 | 2026-09-08 | PL-001 | 4210 | 4217.5 |  | 0.5 | Sample operator A | IT-001
PH-002 | 2026-09-08 | PL-002 | 880 | 883 |  | 1 | Sample operator B | IT-001
PH-003 | 2026-09-09 | PL-001 | 4217.5 | 4225 |  | 0 | Sample operator A | IT-001
PH-004 | 2026-09-09 | PL-002 | 883 | 888.5 |  | 0 | Sample operator B | IT-001
PH-005 | 2026-09-10 | PL-001 | 4225 | 4231 |  | 1 | Sample operator A | IT-001
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.