## RFIs
RFIS
RFIs and technical queries. A variation that comes from one names its RFI ID. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
RFI ID | Date raised | Raised by | To | Question | Item ID | Response needed by | Date answered | Response | Variation ID | Status
RFI-001 | 2026-09-28 | Sample site engineer | Sample Design (engineer) | Kitchen wall cabinets: what blocking is needed? | IT-002 | 2026-10-02 | 2026-10-01 | Two rows of 90 x 45 blocking, see SI-004. | V01
RFI-002 | 2026-10-12 | Sample Sparks | Sample Design (engineer) | Units 3 to 6: confirm the new power point positions. | IT-004 | 2026-10-19 |  |  | V02
RFI-003 | 2026-11-04 | Sample site manager | Sample Design (engineer) | Cladding: cavity batten spacing at the corners. | IT-005 | 2026-11-13
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.
Formulas:
Status = IF([RFI ID]="","",IF([Date answered]<>"","Answered",IF(AND([Response needed by]<>"",TODAY()>[Response needed by]),"Overdue: unanswered","Open")))

## Variations
VARIATIONS
The variations register, with the notice date, the RFI and the item each one comes from. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Var no | Rev | Description | Instruction / ref | Submitted | Approved | Status | Quoted $ | Approved $ | Claimed to date $ | Notes | Contract | Claim no | Notice date | RFI ID | Item ID | Diary ID | Notice recorded | RFI found
V01 | A | Extra blocking to kitchen walls | SI-004 | 2026-10-02 | 2026-10-09 | Approved | 1850 | 1850 |  |  | 12 Example Street townhouses (made-up sample) |  | 2026-10-02 | RFI-001 | IT-002 | D-004
V02 | A | Relocate power points, units 3 to 6 | Email 12 Oct | 2026-10-13 |  | Pending | 640 |  |  |  | 12 Example Street townhouses (made-up sample) |  |  | RFI-002 | IT-004
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.