## Diary index
DIARY INDEX
One row per site diary entry, with the item IDs worked on and the photo references. Type or paste into the white columns; the shaded ones are formulas. Example rows are made up.
Diary ID | Date | Weather | Labour | People on site | Plant | Item IDs | Work done | Delays | Delay cause | Instructions | Visitors | Photo refs | Prepared by
D-001 | 2026-09-25 | Fine | Concrete crew 6, labourers 2 | 8 | Concrete pump, 5 t digger | IT-001 | Slab poured, blocks A and B. |  |  |  | Engineer's slab inspection (Sample Design) | P-0101, P-0102 | Sample site manager
D-004 | 2026-10-16 | Showers | Carpenters 5, labourers 1 | 6 | Telehandler | IT-002 | Level 1 walls framed, blocks A and B. | 1 hour lost to rain | Weather | SI-004: extra blocking to kitchen walls |  | P-0144 | Sample site manager
D-006 | 2026-10-30 | Fine | Carpenters 5, electricians 2 | 7 | Telehandler, scissor lift | IT-002, IT-004 | Roof trusses up, block A. Electrical rough-in, units 1 and 2. |  |  |  | Client's representative site walk | P-0160, P-0161 | Sample site manager
D-007 | 2026-11-02 | Wind | Carpenters 4, roofers 3 | 7 | Telehandler | IT-002, IT-003 | Framing, block B. Roofing started, block A. | Roofing stopped from 2 pm: wind over 50 km/h | Weather |  |  | P-0170 | Sample site manager
D-008 | 2026-11-04 | Fine | Carpenters 4, roofers 3 | 7 | Telehandler | IT-002, IT-003 | Framing, block B. Roofing, block A. |  |  | RFI-003 raised: cladding cavity battens |  | P-0175 | Sample site manager
Free template from Black Creek Solutions (blackcreek.co.nz). Information, not legal advice. Check it against your contract before you use it.